## SUMMARY
PROJECT ID:
DATE:
AREA SUMMARY:
No Of Floors | 3
BUILDING GM2 | 943.61
Basemet (M2) | 376.14
Ground Floor (M2) | 291.66
First Floor (M2) | 275.81
DIVISION NO. | DESCRIPTION | TOTAL DIV. COST | COST/ M2
Division 1 | Preliminaries | 122236.32 | 129.5411
Division 2 | Excavation & Site Levelling | 8872.0809 | 9.4023
Division 3 | Formwork | 36539.5112 | 38.7231
Division 4 | Concrete Supply & Install | 137613.9721 | 145.8378
Division 5 | Termite Treatment | 8244.163 | 8.7368
Division 6 | Carpentry Framing | 171331.7561 | 181.5705
Division 7 | Sarking & Insulation | 36826.9172 | 39.0277
Division 8 | Timber/Steel Stair Frame | 1476.4954 | 1.5647
Division 9 | Masonry Supply & Install | 12658.3759 | 13.4148
Division 10 | Scaffold | 8044.2978 | 8.525
Division 11 | Aluminium Windows & Doors | 238609.2904 | 252.8685
Division 12 | Roofing (Metal/Tiles) | 31072.9572 | 32.9299
Division 13 | Solar Panel | 3721.4643 | 3.9439
Division 14 | Skylights | 556.4907 | 0.58975
Division 15 | Cladding | 17484.5599 | 18.5294
Division 16 | Render | 8288.9592 | 8.7843
Division 17 | Plasterboard | 78615.1226 | 83.3132
Division 18 | External Balustrades | 17216.8052 | 18.2457
Division 19 | Sundry Metalwork (e.g. Garage Door) | 5577.4152 | 5.9107
Division 20 | Door & Hardware Supply & Install | 157973.3717 | 167.4138
Division 21 | Carpentry Fitout | 20535.2108 | 21.7624
Division 22 | Waterproofing | 1909.3541 | 2.0235
Division 23 | Tiling (Supply & Install) | 30655.6902 | 32.4877
Division 24 | Flooring | 46635.9206 | 49.4229
Division 25 | Painting | 85606.3159 | 90.7221
Division 26 | Joinery | 82253.4914 | 87.1689
Division 27 | Shower Screens/ Partition | 13036.2096 | 13.8153
Division 28 | PC Items | 54449.9748 | 57.7039
Division 29 | Appliances | 41625.8458 | 44.1134
Division 30 | Hydraulic Services | 146907.2483 | 155.6864
Division 31 | Electrical Services | 68506.3066 | 72.6002
Division 32 | Mechanical Services | 71664.4915 | 75.9472
Division 33 | Fire Services | 59075.9731 | 62.6063
Division 34 | Civil Works | 33813.4582 | 35.8341
Division 35 | Landscaping | 9285.8692 | 9.8408
Division 36 | Window Shroud | 5719.9572 | 6.0618
TOTAL TRADE COST |  | 1874641.6433 | 1986.67
SUBTOTAL |  | 1874641.6433
OVERHEADS & PROFITS | 25% | 468660.4108
INSURANCES | 3% | 56239.2493
CONTINGENCY | 7% | 131224.915
TOTAL BASE BID |  | 4405407.8617 | 4668.6744

## TAKEOFF
Project
ADDRESS
Date of submission
Date of plans
SITE ESTIMATE
SR # | DESCRIPTION | QUANTITY | UNIT | WASTAGE | QTY W/ WASTE | RATE | TOTAL COST | TRADE COST
Preliminaries
1 | Labor | 1 | EA | 0% | 1 | 0 | 0
2 | Supervision | 1 | EA | 0% | 1 | 42500 | 42500
3 | Authorities & Fees | 1 | EA | 0% | 1 | 0 | 0
4 | Contractors and QBSA Insurances | 1 | EA | 0% | 1 | 0 | 0
5 | Emergency Efficiency Reports | 1 | EA | 0% | 1 | 0 | 0
6 | Building Design \ Drafting | 1 | EA | 0% | 1 | 0 | 0
7 | Color Consultant | 1 | EA | 0% | 1 | 0 | 0
8 | Engineer | 1 | EA | 0% | 1 | 0 | 0
9 | Offices & Sheds | 1 | EA | 0% | 1 | 0 | 0
10 | Bank Charges | 1 | EA | 0% | 1 | 0 | 0
11 | Temp Plumbing | 1 | EA | 0% | 1 | 0 | 0
12 | Temp Power | 1 | EA | 0% | 1 | 0 | 0
13 | Temp Comms | 1 | EA | 0% | 1 | 0 | 0
14 | Temp Roads | 1 | EA | 0% | 1 | 0 | 0
15 | Temp Fencing | 1 | EA | 0% | 1 | 0 | 0
16 | Toilet Hire | 1 | EA | 0% | 1 | 0 | 0
17 | Man MATerials | 1 | EA | 0% | 1 | 0 | 0
18 | Craneage | 1 | EA | 0% | 1 | 0 | 0
19 | Major Plant | 1 | EA | 0% | 1 | 0 | 0
20 | Minor Plant | 1 | EA | 0% | 1 | 0 | 0
21 | Contour and Site Survey | 1 | EA | 0% | 1 | 23040 | 23040
22 | Tools & Site Equipment | 1 | EA | 0% | 1 | 25758.72 | 25758.72
23 | First Aid | 1 | EA | 0% | 1 | 0 | 0
24 | Safety Precautions | 1 | EA | 0% | 1 | 0 | 0
25 | Cleaning During Construction | 1 | EA | 0% | 1 | 0 | 0
26 | Cleaning on Completion | 1 | EA | 0% | 1 | 17337.6 | 17337.6
27 | OperATing Supplies | 1 | EA | 0% | 1 | 0 | 0
28 | Security | 1 | EA | 0% | 1 | 13600 | 13600
Sub Total | [7 empty] | 122236.32
Excavation & Site Levelling
Detailed Excavation
Cut
29 | Drilling For Bored Pier | 123 | M | 0% | 123 | 20.64 | 2538.72
30 | Earthwork In Cut For Strip Footing | 8.6 | M3 | 0% | 8.6 | 24.768 | 213.0048
31 | Earthwork In Cut For Pad Footing | 19.2 | M3 | 0% | 19.2 | 24.768 | 475.5456
32 | Earthwork In Cut For Edge Beam | 7.9074 | M3 | 0% | 7.9074 | 24.768 | 195.8505
Site Clearance
33 | Site Clearance | 660 | M2 | 0% | 660 | 8.256 | 5448.96
Sub Total | [7 empty] | 8872.0809
Formwork
Formwork
Basement
Edge Of Slab
34 | (155mm H) Edge Of Slab | 20.31 | M | 0% | 20.31 | 24.768 | 503.0381
35 | (125mm H) Edge Of Slab | 86.29 | M | 0% | 86.29 | 19.9742 | 1723.5732
Stair
36 | Stair Riser Formwork | 10.92 | M | 0% | 10.92 | 44.9553 | 490.9117
Strip Footing
37 | Strip Footing Formwork | 24 | M2 | 0% | 24 | 44.9553 | 1078.9267
Pad Footing
38 | Pad Footing Formwork | 19.2 | M2 | 0% | 19.2 | 44.9553 | 863.1414
Shotcrete Wall
39 | Shotcrete Wall Formwork | 207.4 | M2 | 0% | 207.4 | 44.9553 | 9323.7251
Column
40 | Concrete Column Formwork | 28.8 | M2 | 0% | 28.8 | 44.9553 | 1294.7121
Edge Beam
41 | Edge Beam Formwork | 52.716 | M2 | 0% | 52.716 | 44.9553 | 2369.8625
Ground Floor
Edge Of Slab
42 | (205mm H) Edge Of Slab | 75.79 | M | 0% | 75.79 | 32.7577 | 2482.7044
43 | (275mm H) Edge Of Slab | 12.49 | M | 0% | 12.49 | 43.9432 | 548.8509
44 | (375mm H) Edge Of Slab | 4.44 | M | 0% | 4.44 | 59.9226 | 266.0563
Step In Slab
45 | (105mm H) Step In Slab | 36.75 | M | 0% | 36.75 | 16.7783 | 616.6034
46 | (175mm H) Step In Slab | 5.76 | M | 0% | 5.76 | 27.9639 | 161.0719
47 | (245mm H) Step In Slab | 52.89 | M | 0% | 52.89 | 39.1494 | 2070.6128
Suspended Slab
48 | Suspended Slab Soffit Formwork | 278.4 | M2 | 0% | 278.4 | 44.9553 | 12515.55
Beam
49 | Beam Formwork | 5.12 | M2 | 0% | 5.12 | 44.9553 | 230.171
Sub Total | [7 empty] | 36539.5112
Concrete Supply & Install
Basement
Bored Pier
50 | (450mm.Dia) Bored Pier 'BP1' Reinforced w/ (3000mm H & 41 EA) - 6N24 (V) + R10 - 300 CTS Ligs - 40 MPa | 123 | M | 0% | 123 | 97.2074 | 11956.5151
Strip Footing
51 | (500 x 600) Strip Footing 'SF2' Reinforced w/ (10.2 LM) - 6N16 T & B + 3N12-250 CTRS Ligs - 25 MPa | 3.051 | M3 | 0% | 3.051 | 451.4 | 1377.2214
52 | (500 x 800) Strip Footing 'SF1' Reinforced w/ (13.9 LM) - 6N16 T & B + 3N12-250 CTRS Ligs 1N12 Mid-Hight E.F - 25 MPa | 5.548 | M3 | 0% | 5.548 | 451.4 | 2504.3672
Pad Footing
53 | (2000 x 2000 x 600) Pad Footing 'PF1' Reinforced w/ (2 EA) - SL81 Top & N20-200 CTRS Bottom Each way, 1N16 Mid-Height E.F - 25 MPa | 9.6 | M3 | 0% | 9.6 | 451.4 | 4333.44
54 | (1200 x 1200 x 600) Pad Footing 'PF2' Reinforced w/ (2 EA) - SL81 Top & N16-200 CTRS Bottom Each way, 1N12 Mid-Height E.F - 25 MPa | 5.76 | M3 | 0% | 5.76 | 451.4 | 2600.064
55 | (2000 x 1200 x 600) Pad Footing 'PF3' Reinforced w/ (1 EA) - SL81 Top & N16-200 CTRS Bottom Each way, 1N16 Mid-Height E.F - 25 MPa | 3.84 | M3 | 0% | 3.84 | 451.4 | 1733.376
Shotcrete Wall
56 | (150mm Thick) Shotcrete Wall 'SCW' Reinforced w/ (39.5 LM & 3150mm H) - RL818 Main Wire Horizontal, Lap 600 - w/ 40MPa | 18.6685 | M3 | 0% | 18.6685 | 451.4 | 8426.9496
57 | (150mm Thick) Shotcrete Wall 'SCW' Reinforced w/ (31.9 LM & 2600mm H) - RL818 Main Wire Horizontal, Lap 600 - w/ 40MPa | 12.4488 | M3 | 0% | 12.4488 | 451.4 | 5619.3883
Column
58 | (250 x 1000) Concrete Column 'CC1' Reinforced w/ (3150mm H & 2 EA) - 8N20 Vert, & 3N12-300 Ligatures, Lap 600, - 40 MPa | 15.75 | M3 | 0% | 15.75 | 451.4 | 7109.55
59 | (250 x 1000) Concrete Column 'CC1' Reinforced w/ (2600mm H & 2 EA) - 8N20 Vert, & 3N12-300 Ligatures, Lap 600, - 40 MPa | 13 | M3 | 0% | 13 | 451.4 | 5868.2
Edge Beam
60 | (300 x 300) Edge Beam Reinforced w/ (87.9 LM) - 3-L11TM | 7.9074 | M3 | 0% | 7.9074 | 451.4 | 3569.4004
Stair
61 | Reinforced Concrete Stair | 0.7944 | M3 | 0% | 0.7944 | 451.4 | 358.5922
Slab On Grade
62 | (100mm Thick) Slab On Grade Reinforced w/ (337.1 M2) - SL82 Mesh - 25 MPa | 33.707 | M3 | 0% | 33.707 | 451.4 | 15215.3398
63 | (130mm Thick) Medium Duty RC Concrete Pavement Slab Reinforced w/ (23.6 M2) - SL82 Mesh - (130mm Thick) Class 2 20mm FCR Compacted To 98% Standard Relative Compacted | 3.0615 | M3 | 0% | 3.0615 | 451.4 | 1381.9611
64 | Saw Cut Joint 'SCJ' | 157.53 | M | 0% | 157.53 | 8.3947 | 1322.4172
Ground Floor
Slab On Grade
65 | (180mm Thick) Slab On Grade Reinforced w/ (16.1 M2) - SL92 Mesh - 32 MPa | 2.9052 | M3 | 0% | 2.9052 | 451.4 | 1311.4073
Suspended Slab
66 | (180mm Thick) Suspended Slab Reinforced w/ (196.5 M2) - SL92 Mesh - 32 MPa | 35.361 | M3 | 0% | 35.361 | 451.4 | 15961.9554
67 | (250mm Thick) Suspended Slab Reinforced w/ (26.6 M2) - SL92 Mesh - 32 MPa | 6.65 | M3 | 0% | 6.65 | 451.4 | 3001.81
68 | (350mm Thick) Suspended Slab Reinforced w/ (55.3 M2) - SL92 Mesh - 32 MPa | 19.369 | M3 | 0% | 19.369 | 451.4 | 8743.1666
Beam
69 | (400 x 400) Reinforced Concrete Beam (6.4 LM) | 1.024 | M3 | 0% | 1.024 | 451.4 | 462.2336
Underlayment's
70 | 50mm Sand Bed | 376.7 | M2 | 0% | 376.7 | 88.228 | 33235.4876
71 | 0.2 Polythene Membrane | 472.616 | M2 | 0% | 472.616 | 3.2185 | 1521.1293
Sub Total | [7 empty] | 137613.9721
Termite Treatment
72 | Termite Treatment | 472.616 | M2 | 0% | 472.616 | 17.4437 | 8244.163
Sub Total | [7 empty] | 8244.163
Carpentry Framing
Floor Framing
Ground Floor
Double Stud
73 | 90 x 45 MGP10 'DS' (2400mm H & 60 EA) | 144 | M | 0% | 144 | 22.5128 | 3241.8501
Lintel
74 | 290 x 45 F17 KDHW Lintel '1L2' - 2 Pieces of 1.3m | 2.6 | M | 0% | 2.6 | 123.627 | 321.4303
75 | 290 x 45 MGP10 Lintel '1L4' - 2 Pieces of 2.9m | 5.8 | M | 0% | 5.8 | 123.627 | 717.0368
76 | 90 x 45 MGP10 Lintel '1L5' - 2 Pieces of 0.7m | 1.4 | M | 0% | 1.4 | 22.5128 | 31.518
77 | 140 x 45 MGP10 Lintel '1L3' - 2 Pieces of 1.1m | 2.2 | M | 0% | 2.2 | 25.5744 | 56.2636
78 | 90 x 45 MGP10 Lintel '1L6' - 2 Pieces of 0.8m | 1.6 | M | 0% | 1.6 | 22.5128 | 36.0206
79 | 140 x 45 MGP10 Lintel '1L7' - 2 Pieces of 1.1m | 2.2 | M | 0% | 2.2 | 25.5744 | 56.2636
80 | 190 x 45 MGP10 Lintel '1L8' - 2 Pieces of 1.6m | 3.2 | M | 0% | 3.2 | 29.7268 | 95.1257
81 | 190 x 45 MGP10 Lintel '1L1' - 2 Pieces of 3.0m | 6 | M | 0% | 6 | 29.7268 | 178.3607
82 | 300 x 90 LVL HYSPAN '2, 3L1' - 2 Pieces of 3.4m | 6.8 | M | 0% | 6.8 | 43.2695 | 294.2328
83 | 90 x 45 MGP10 '2, 3L2' - 4 Pieces of 0.7m | 2.86 | M | 0% | 2.86 | 22.5128 | 64.3867
84 | 90 x 45 MGP10 '2, 3L3' - 4 Pieces of 0.7m | 2.8 | M | 0% | 2.8 | 22.5128 | 63.036
85 | 190 x 45 MGP10 '2, 3L4' - 4 Pieces of 1.6m | 6.4 | M | 0% | 6.4 | 29.7268 | 190.2514
86 | 140 x 45 MGP10 '2, 3L5' - 4 Pieces of 1.1m | 4.28 | M | 0% | 4.28 | 25.5744 | 109.4583
87 | 240 x 45 MGP10 '2, 3L6' - 4 Pieces of 2.3m | 9.2 | M | 0% | 9.2 | 37.3127 | 343.2771
88 | 300 x 90 LVL HYSPAN '4L1' - 1 Piece of 3.7m | 3.72 | M | 0% | 3.72 | 43.2695 | 160.9626
89 | 120 x 45 MGP10 '4L2' - 2 Pieces of 0.7m | 1.38 | M | 0% | 1.38 | 21.6285 | 29.8474
90 | 120 x 45 MGP10 '4L3' - 2 Pieces of 0.8m | 1.64 | M | 0% | 1.64 | 21.6285 | 35.4708
91 | 360 x 90 LVL HYSPAN OR 180PEC '4L4' - 1 Piece of 2.2m | 2.15 | M | 0% | 2.15 | 52.632 | 113.1588
92 | 190 x 45 MGP10 '4L8' - 2 Pieces of 1.6m | 3.18 | M | 0% | 3.18 | 29.3053 | 93.1909
93 | 140 x 45 MGP10 '4L9' - 2 Pieces of 1.1m | 2.2 | M | 0% | 2.2 | 25.5744 | 56.2636
Beam
94 | 300 x 90 LVL Hyspan '1B1' - 1 Piece of 4.1m | 4.11 | M | 0% | 4.11 | 43.2695 | 177.8377
95 | 400 x 90 LVL Hyspan or 200 PFC '1B2' - 1 Piece of 4.9m | 4.94 | M | 0% | 4.94 | 55.5762 | 274.5466
96 | 400 x 90 LVL Hyspan or 200 PFC '1B3' - 1 Piece of 5.9m | 5.91 | M | 0% | 5.91 | 55.5762 | 328.4556
97 | 300 x 90 LVL Hyspan 'IB4' - 1 Piece of 1.8m | 1.79 | M | 0% | 1.79 | 43.2695 | 77.4524
98 | 300 x 90 LVL HYSPAN '1B5' - 1 Piece of 1.8m | 1.79 | M | 0% | 1.79 | 43.2695 | 77.4524
99 | 290 x 45 MGP10 '1B6' - 2 Pieces of 3.3m | 6.5 | M | 0% | 6.5 | 123.627 | 803.5758
100 | 170 x 45 MGP10 '1B7' - 2 Pieces of 1.7m | 3.4 | M | 0% | 3.4 | 27.551 | 93.6735
101 | 240 x 45 MGP10 '1B8' - 2 Pieces of 2.3m | 4.5 | M | 0% | 4.5 | 37.3127 | 167.9073
102 | 240 x 45 MGP10 '1B9' - 2 Pieces of 1m | 1.92 | M | 0% | 1.92 | 37.3127 | 71.6404
103 | 120 x 45 MGP10 '1B10' - 2 Pieces of 1.1m | 2.26 | M | 0% | 2.26 | 21.6285 | 48.8805
104 | 240 x 45 MGP10 '1B11' - 2 Pieces of 2.9m | 5.7 | M | 0% | 5.7 | 37.3127 | 212.6826
105 | 240 x 45 MGP10 EXTEND 1000MM INPARTY WALL '1B12' - 2 Pieces of 1.3m | 2.6 | M | 0% | 2.6 | 37.3127 | 97.0131
106 | 300 x 90 LVL HYSPAN '2, 3B1' - 2 Pieces of 4m | 8 | M | 0% | 8 | 43.2695 | 346.1562
107 | 300 x 90 LVL HYSPAN '2, 3B2' - 2 Pieces of 2.6m | 5.19 | M | 0% | 5.19 | 43.2695 | 224.5688
108 | 300 x 90 LVL HYSPAN '2, 3B3' - 2 Pieces of 2.6m | 5.23 | M | 0% | 5.23 | 43.2695 | 226.2996
109 | 310UB32 OR 300PEC '2, 3B4' - 2 Pieces of 7m | 14 | M | 0% | 14 | 43.2695 | 605.7733
110 | 140 x 45 MGP10 '2, 3B5' - 4 Pieces of 1.1m | 4.4 | M | 0% | 4.4 | 25.5744 | 112.5272
111 | 140 x 45 MGP10 '2, 3B6' - 4 Pieces of 1.3m | 5.2 | M | 0% | 5.2 | 25.5744 | 132.9867
112 | 140 x 45 MGP10 '2, 3B7' - 4 Pieces of 1.1m | 4.4 | M | 0% | 4.4 | 25.5744 | 112.5272
113 | 240 x 45 MGP10 '2, 3B8' - 4 Pieces of 2.1m | 8.4 | M | 0% | 8.4 | 37.3127 | 313.4269
114 | 120 x 45 MGP10 '2, 3B9' - 4 Pieces of 1.1m | 4.34 | M | 0% | 4.34 | 21.6285 | 93.8678
115 | 140 x 45 MGP10 '2, 3B10' - 4 Pieces of 0.6m | 2.4 | M | 0% | 2.4 | 25.5744 | 61.3785
116 | 240 x 45 MGP10 EXTEND 1000MM IN PARTY WALL '2, 3B11' - 4 Pieces of 1.4m | 5.6 | M | 0% | 5.6 | 37.3127 | 208.9513
117 | 140 x 45 MGP10 EXTEND 1000MM IN & TIE FLOOR '2, 3B12' - 4 Piece of 0.9m | 3.6 | M | 0% | 3.6 | 25.5744 | 92.0677
118 | 240 x 45 MGP10 'B1' - 4 Pieces of 1.4m - 2 Pieces of 1.5m - 2 Pieces of 1.6m - 4 Pieces of 2m | 19.8 | M | 0% | 19.8 | 37.3127 | 738.7921
119 | 240 x 45 MGP10 'B2' - 4 Pieces of 1.3m | 5.2 | M | 0% | 5.2 | 37.3127 | 194.0262
120 | 240 x 45 MGP10 'B3' - 2 Pieces of 1.1m | 2.24 | M | 0% | 2.24 | 37.3127 | 83.5805
121 | 300 x 90 LVL HYSPAN '4B1' - 1 Piece of 4.2m | 4.18 | M | 0% | 4.18 | 43.2695 | 180.8666
122 | 300 x 90 LVL HYSPAN '4B2' - 1 Piece of 2.6m | 2.57 | M | 0% | 2.57 | 43.2695 | 111.2027
123 | 300 x 90 LVL HYSPAN '4B3' - 1 Piece of 3.3m | 3.34 | M | 0% | 3.34 | 43.2695 | 144.5202
124 | 310UB32 OR 300PEC '4B4' - 1 Piece of 7.1m | 7.12 | M | 0% | 7.12 | 43.2695 | 308.079
125 | 120 x 45 MGP10 '4B5' - 2 Pieces of 1m | 1.94 | M | 0% | 1.94 | 21.6285 | 41.9593
126 | 140 x 45 MGP10 '4B6' - 2 Pieces of 1.3m | 2.6 | M | 0% | 2.6 | 25.5744 | 66.4934
127 | 140 x 45 MGP10 '4B7' - 2 Pieces of 1.2m | 2.38 | M | 0% | 2.38 | 25.5744 | 60.867
128 | 290 x F17 KDHW '4B8' - 2 Pieces of 3.1m | 6.2 | M | 0% | 6.2 | 123.627 | 766.4876
129 | 290 x F17 KDHW '4B9' - 2 Pieces of 0.6m | 1.2 | M | 0% | 1.2 | 123.627 | 148.3524
130 | 190 x 45 MGP10 '4B10' - 2 Pieces of 0.6m | 1.14 | M | 0% | 1.14 | 29.3053 | 33.4081
131 | 240 x 45 MGP10 '4B11' - 2 Pieces of 2.2m | 4.38 | M | 0% | 4.38 | 37.3127 | 163.4298
132 | 190 x 45 MGP10 CONTINUOUS TWO SPANS '4B12' - 2 Pieces of 1.9m | 3.78 | M | 0% | 3.78 | 29.7268 | 112.3673
133 | 240 x 45 MGP10 '4B13' - 2 Pieces of 2.1m | 4.2 | M | 0% | 4.2 | 37.3127 | 156.7135
134 | 120 x 45 MGP10 '4B14' - 2 Pieces of 1.1m | 2.22 | M | 0% | 2.22 | 21.6285 | 48.0153
135 | 140 x 45 MGP10 '4B15' - 2 Pieces of 0.6m | 1.18 | M | 0% | 1.18 | 25.5744 | 30.1778
136 | 140 x 45 MGP10 EXTEND 1000MM IN & TIE FLOOR '4B16' - 2 Pieces of 0.7m | 1.32 | M | 0% | 1.32 | 25.5744 | 33.7582
137 | 369 x 90 LVL HYSPAN OR 180PFC '4B17' - 1 Piece of 3.7m | 3.69 | M | 0% | 3.69 | 55.5762 | 205.0763
138 | 240 x 45 MGP10 EXTEND 1000MM IN PARTY WALL '4B18' - 2 Pieces of 1.3m | 2.68 | M | 0% | 2.68 | 37.3127 | 99.9981
Floor Beam
139 | 300 x 90 LVL HYSPAN 'FB1' - 4 Pieces of 1.1m | 4.4 | M | 0% | 4.4 | 43.2695 | 190.3859
140 | 301 x 90 LVL HYSPAN 'FB2 - 4 Pieces of 0.7m | 2.8 | M | 0% | 2.8 | 43.2695 | 121.1547
141 | 302 x 90 LVL HYSPAN 'FB3' - 4 Pieces of 0.7m | 2.8 | M | 0% | 2.8 | 43.2695 | 121.1547
Floor Trusses
142 | 350mm DEEP DOSI-STRUT TIMBER FLOOR TRUSSES 'FJ1' (277.2 M2) - 9 Pieces of 1m - 3 Pieces of 1.1m - 2 Pieces of 2.9m - 4 Pieces of 3.3m - 14 Pieces of 3.4m - 6 Pieces of 3.5m - 3 Pieces of 4m - 4 Pieces of 4.3m - 16 Pieces of 4.5m - 7 Pieces of 5m - 3 Pieces of 5.1m - 4 Pieces of 5.5m - 1 Piece of 5.7m - 3 Pieces of 6.2m - 1 Piece of 10.2m - 5 Pieces of 10.3m - 12 Pieces of 10.5m - 8 Pieces of 10.6m - 6 Pieces of 10.7m - 2 Pieces of 10.8m | 655.1 | M | 0% | 655.1 | 46.1373 | 30224.5321
Floor Covering
143 | Tongue & Groove Floor Covering | 277.2 | M2 | 0% | 277.2 | 9.9072 | 2746.2758
Mullion
144 | 90 x 90 F17 KDHW POST 'M1' (2600mm H & 1 EA) | 2.6 | M | 0% | 2.6 | 12.7827 | 33.2351
Roof Framing
Ground Floor
Lintel
145 | 240 x 45 MGP10 '4L5' - 2 Pieces of 3.1m | 6.2 | M | 0% | 6.2 | 37.3127 | 231.3389
146 | 190 x 45 MGP10 '4L6' - 2 Pieces of 1.3m | 2.64 | M | 0% | 2.64 | 29.7268 | 78.4787
147 | 360 x 90 LVL HYSPAN OR 180PEC '4L7' - 1 Piece of 2.8m | 2.79 | M | 0% | 2.79 | 123.627 | 344.9194
148 | 140 x 45 MGP10 '4L10' - Pieces of 0.8m | 1.5 | M | 0% | 1.5 | 25.5744 | 38.3616
149 | 140 x 45 MGP10 '4L11' - 2 Pieces of 0.8m | 1.56 | M | 0% | 1.56 | 25.5744 | 39.896
Roof
Roof Lintel
150 | 90 x 45 MGP10 '1RL1' - 2 Pieces of 0.8m | 1.6 | M | 0% | 1.6 | 22.5128 | 36.0206
151 | 90 x 45 MGP10 '1RL2' - 2 Pieces of 0.7m | 1.4 | M | 0% | 1.4 | 22.5128 | 31.518
152 | 290 x 45 MGP10 '1RL3' - 2 Pieces of 4.4m | 8.8 | M | 0% | 8.8 | 123.627 | 1087.918
153 | 240 x 45 MGP10 '1RL4' - 2 Pieces of 3m | 6 | M | 0% | 6 | 37.3127 | 223.8764
154 | 120 x 45 MGP10 '1RL5' - 2 Pieces of 1.3m | 2.64 | M | 0% | 2.64 | 21.6285 | 57.0993
155 | 140 x 45 MGP10 '1RL6' - 2 Pieces of 1.6m | 3.16 | M | 0% | 3.16 | 25.5744 | 80.815
156 | 240 x 45 MGP10 '1RL7' - 2 Pieces of 2.7m | 5.4 | M | 0% | 5.4 | 37.3127 | 201.4887
157 | 90 x 45 MGP10 '1RL8' - 2 Pieces of 0.7m | 1.4 | M | 0% | 1.4 | 22.5128 | 31.518
158 | 90 x 45 MGP10 '1RL9' - 2 Pieces of 0.8m | 1.6 | M | 0% | 1.6 | 22.5128 | 36.0206
159 | 240 x 45 MGP10 '1RL10' - 2 Pieces of 2.7m | 5.4 | M | 0% | 5.4 | 37.3127 | 201.4887
160 | 240 x 45 MGP10 '2, 3RL1' - 4 Pieces of 2.7m | 10.8 | M | 0% | 10.8 | 37.3127 | 402.9775
161 | 190 x 45 MGP10 '2, 3RL2' - 4 Pieces of 2.3m | 9.2 | M | 0% | 9.2 | 29.7268 | 273.4864
162 | 240 x 45 MGP10 '2, 3RL3' - 4 Pieces of 2.7m | 10.8 | M | 0% | 10.8 | 37.3127 | 402.9775
163 | 90 x 45 MGP10 '2, 3RL4' - 4 Pieces of 0.7m | 2.72 | M | 0% | 2.72 | 22.5128 | 61.2349
164 | 90 x 45 MGP10 '2, 3RL5' - 4 Pieces of 0.7m | 2.72 | M | 0% | 2.72 | 22.5128 | 61.2349
165 | 240 x 45 MGP10 '4RL1' - 2 Pieces of 2.7m | 5.32 | M | 0% | 5.32 | 37.3127 | 198.5037
166 | 190 x 45 MGP10 '4RL2' - 2 Pieces of 2.2m | 4.32 | M | 0% | 4.32 | 29.7268 | 128.4197
167 | 240 x 45 MGP10 '4RL3' - 2 Pieces of 2.7m | 5.3 | M | 0% | 5.3 | 37.3127 | 197.7575
168 | 90 x 45 MGP10 '4RL4' - 2 Pieces of 0.7m | 1.46 | M | 0% | 1.46 | 22.5128 | 32.8688
169 | 90 x 45 MGP10 '4RL5' - 2 Pieces of 0.7m | 1.36 | M | 0% | 1.36 | 22.5128 | 30.6175
170 | 90 x 45 MGP10 '4RL6' - 2 Pieces of 0.7m | 1.42 | M | 0% | 1.42 | 22.5128 | 31.9682
171 | 90 x 45 MGP10 '4RL7' - 2 Pieces of 0.7m | 1.42 | M | 0% | 1.42 | 22.5128 | 31.9682
172 | 90 x 45 MGP10 '4RL8' - 2 Pieces of 0.9m | 1.84 | M | 0% | 1.84 | 22.5128 | 41.4236
173 | 90 x 45 MGP10 '4RL9' - 2 Pieces of 0.9m | 1.76 | M | 0% | 1.76 | 22.5128 | 39.6226
174 | 90 x 45 MGP10 '4RL10' - 2 Pieces of 0.7m | 1.36 | M | 0% | 1.36 | 22.5128 | 30.6175
175 | 90 x 45 MGP10 '4RL11' - 2 Pieces of 0.7m | 1.44 | M | 0% | 1.44 | 22.5128 | 32.4185
Roof Beam
176 | 140 x 45 MGP10 '2,3PB1' - 2 Pieces of 1.1m - 1 Piece of 1.3m - 1 Piece of 1.4m | 4.9 | M | 0% | 4.9 | 25.5744 | 125.3144
177 | 190 x 45 F17 KDHW '2,3PB2' - 2 Pieces of 3m - 2 Pieces of 3.2m | 12.4 | M | 0% | 12.4 | 29.7268 | 368.6121
178 | 190 x 45 F17 KDHW '2,3PB3' - 2 Pieces of 2.9m - 2 Pieces of 3.1m | 12 | M | 0% | 12 | 29.7268 | 356.7214
179 | 190 x 45 F17 KDHW '3PB4' - 2 Pieces of 2.1m | 4.2 | M | 0% | 4.2 | 29.7268 | 124.8525
180 | 140 x 45 MGP10 '4PB1' - 2 Pieces of 1.3m | 2.6 | M | 0% | 2.6 | 25.5744 | 66.4934
181 | 190 x 45 F17 KDHW '4PB2' - 2 Pieces of 3.1m | 6.2 | M | 0% | 6.2 | 29.7268 | 184.3061
182 | 190 x 45 F17 KDHW '4PB3' - 2 Pieces of 3.1m | 6.2 | M | 0% | 6.2 | 29.7268 | 184.3061
183 | 190 x 45 F17 KDHW '4PB4' - 2 Pieces of 2.1m | 4.2 | M | 0% | 4.2 | 29.7268 | 124.8525
Trusses
184 | Timber Lower Roof Trusses At 600 CTRS By Manufacture Specs | 8.65 | M2 | 0% | 8.65 | 12.384 | 107.1216
185 | Timber Upper Roof Trusses At 600 CTRS By Manufacture Specs | 279.82 | M2 | 0% | 279.82 | 12.384 | 3465.2909
Double Stud
186 | 90 x 45 MGP10 'DS' (2400mm H & 52 EA) | 124.8 | M | 0% | 124.8 | 22.5128 | 2809.6034
Wall Framing
Ground Floor
External Double Stud Wall (26.7 LM & 400mm H)
187 | 90 x 45 MGP10 Timber Stud At 450 CTRS (122 EA & 11 M2) | 48.8 | M | 0% | 48.8 | 22.5128 | 1098.627
188 | 90 x 45 Top Plate | 26.7 | M | 0% | 26.7 | 22.5128 | 601.093
189 | 90 x 35 Ribbon Plate | 26.7 | M | 0% | 26.7 | 22.5128 | 601.093
190 | 90 x 45 Bottom Plate | 26.7 | M | 0% | 26.7 | 22.5128 | 601.093
External Double Stud Wall (50.2 LM & 2750mm H)
191 | 90 x 45 MGP10 Timber Stud At 450 CTRS (226 EA & 139 M2) | 621.5 | M | 0% | 621.5 | 22.5128 | 13991.735
192 | 90 x 45 Top Plate | 50.2 | M | 0% | 50.2 | 22.5128 | 1130.145
193 | 90 x 35 Ribbon Plate | 50.2 | M | 0% | 50.2 | 22.5128 | 1130.145
194 | 90 x 45 Bottom Plate | 50.2 | M | 0% | 50.2 | 22.5128 | 1130.145
195 | 90 x 45 Noggings At 1350 CTRS | 50.2 | M | 0% | 50.2 | 22.5128 | 1130.145
Internal Double Stud Party Wall (24.3 LM & 2750mm H)
196 | 90 x 45 MGP10 Timber Stud At 450 CTRS (110 EA & 67 M2) | 302.5 | M | 0% | 302.5 | 22.5128 | 6810.1365
197 | 90 x 45 Top Plate | 24.3 | M | 0% | 24.3 | 22.5128 | 547.0622
198 | 90 x 35 Ribbon Plate | 24.3 | M | 0% | 24.3 | 22.5128 | 547.0622
199 | 90 x 45 Bottom Plate | 24.3 | M | 0% | 24.3 | 22.5128 | 547.0622
200 | 90 x 45 Noggings At 1350 CTRS | 24.3 | M | 0% | 24.3 | 22.5128 | 547.0622
Internal Single Stud Wall (10.1 LM & 400mm H)
201 | 90 x 45 MGP10 Timber Stud At 450 CTRS (24 EA & 5 M2) | 9.6 | M | 0% | 9.6 | 22.5128 | 216.1233
202 | 90 x 45 Top Plate | 10.08 | M | 0% | 10.08 | 22.5128 | 226.9295
203 | 90 x 35 Ribbon Plate | 10.08 | M | 0% | 10.08 | 22.1628 | 223.4015
204 | 90 x 45 Bottom Plate | 10.08 | M | 0% | 10.08 | 22.5128 | 226.9295
Internal Single Stud Wall (112.7 LM & 2750mm H)
205 | 90 x 45 MGP10 Timber Stud At 450 CTRS (252 EA & 310 M2) | 693 | M | 0% | 693 | 22.5128 | 15601.4037
206 | 90 x 45 Top Plate | 112.7 | M | 0% | 112.7 | 22.5128 | 2537.198
207 | 90 x 35 Ribbon Plate | 112.7 | M | 0% | 112.7 | 22.1628 | 2497.753
208 | 90 x 45 Bottom Plate | 112.7 | M | 0% | 112.7 | 22.5128 | 2537.198
209 | 90 x 45 Noggings At 1350 CTRS | 112.7 | M | 0% | 112.7 | 22.5128 | 2537.198
First Floor
External Double Stud Party Wall (4.7 LM & 3100mm H)
210 | 90 x 45 MGP10 Timber Stud At 450 CTRS (24 EA & 15 M2) | 74.4 | M | 0% | 74.4 | 22.5128 | 1674.9559
211 | 90 x 45 Top Plate | 4.65 | M | 0% | 4.65 | 22.5128 | 104.6847
212 | 90 x 35 Ribbon Plate | 4.65 | M | 0% | 4.65 | 22.5128 | 104.6847
213 | 90 x 35 Bottom Plate | 4.65 | M | 0% | 4.65 | 22.5128 | 104.6847
214 | 90 x 45 Noggings At 1350 CTRS | 4.65 | M | 0% | 4.65 | 22.5128 | 104.6847
External Single Stud Wall (20.2 LM & 1000mm H)
215 | 90 x 45 MGP10 Timber Stud At 450 CTRS (46 EA & 21 M2) | 46 | M | 0% | 46 | 22.5128 | 1035.591
216 | 90 x 45 Top Plate | 20.2 | M | 0% | 20.2 | 22.5128 | 454.7595
217 | 90 x 35 Ribbon Plate | 20.2 | M | 0% | 20.2 | 22.1628 | 447.6895
218 | 90 x 35 Bottom Plate | 20.2 | M | 0% | 20.2 | 22.1628 | 447.6895
219 | 90 x 45 Noggings At 1350 CTRS | 20.2 | M | 0% | 20.2 | 22.5128 | 454.7595
External Single Stud Wall (59.5 LM & 3100mm H)
220 | 90 x 45 MGP10 Timber Stud At 450 CTRS (134 EA & 185 M2) | 415.4 | M | 0% | 415.4 | 22.5128 | 9351.8371
221 | 90 x 45 Top Plate | 59.5 | M | 0% | 59.5 | 22.5128 | 1339.5145
222 | 90 x 35 Ribbon Plate | 59.5 | M | 0% | 59.5 | 22.1628 | 1318.6895
223 | 90 x 35 Bottom Plate | 59.5 | M | 0% | 59.5 | 22.1628 | 1318.6895
224 | 90 x 45 Noggings At 1350 CTRS | 59.5 | M | 0% | 59.5 | 22.5128 | 1339.5145
Internal Single Stud Wall (101 LM & 2600mm H)
225 | 90 x 45 MGP10 Timber Stud At 450 CTRS (226 EA & 263 M2) | 587.6 | M | 0% | 587.6 | 22.5128 | 13228.5495
226 | 90 x 45 Top Plate | 101 | M | 0% | 101 | 22.5128 | 2273.7976
227 | 90 x 35 Ribbon Plate | 101 | M | 0% | 101 | 22.1628 | 2238.4476
228 | 90 x 35 Bottom Plate | 101 | M | 0% | 101 | 22.1628 | 2238.4476
229 | 90 x 45 Noggings At 1350 CTRS | 101 | M | 0% | 101 | 22.5128 | 2273.7976
Internal Double Stud Party Wall (15.6 LM & 3100mm H)
230 | 90 x 45 MGP10 Timber Stud At 450 CTRS (72 EA & 49 M2) | 223.2 | M | 0% | 223.2 | 22.5128 | 5024.8677
231 | 90 x 45 Top Plate | 15.6 | M | 0% | 15.6 | 22.5128 | 351.2004
232 | 90 x 35 Ribbon Plate | 15.6 | M | 0% | 15.6 | 22.1628 | 345.7404
233 | 90 x 35 Bottom Plate | 15.6 | M | 0% | 15.6 | 22.1628 | 345.7404
234 | 90 x 45 Noggings At 1350 CTRS | 15.6 | M | 0% | 15.6 | 22.5128 | 351.2004
Internal Double Stud Party Wall (10.5 LM & 3600mm H)
235 | 90 x 45 F17 KDHW Timber Stud At 450 CTRS (50 EA & 38 M2) | 180 | M | 0% | 180 | 22.5128 | 4052.3126
236 | 90 x 45 Top Plate | 10.5 | M | 0% | 10.5 | 22.5128 | 236.3849
237 | 90 x 35 Ribbon Plate | 10.5 | M | 0% | 10.5 | 22.1628 | 232.7099
238 | 90 x 35 Bottom Plate | 10.5 | M | 0% | 10.5 | 22.1628 | 232.7099
239 | 90 x 45 Noggings At 1350 CTRS | 10.5 | M | 0% | 10.5 | 22.5128 | 236.3849
Sub Total | [7 empty] | 171331.7561
Sarking & InsulaTion
Wall
Ground Floor
240 | Internal Wall Insulation (If.Req) | 381 | M2 | 0% | 381 | 15.8775 | 6049.3107
241 | External Wall Insulation | 149 | M2 | 0% | 149 | 18.0845 | 2694.5975
242 | Sealant | 742 | M | 0% | 742 | 3.9552 | 2934.7252
First Floor
243 | Internal Wall Insulation (If.Req) | 349 | M2 | 0% | 349 | 15.8775 | 5541.2321
244 | External Wall Insulation | 205 | M2 | 0% | 205 | 18.0845 | 3707.3322
245 | Sealant | 668 | M | 0% | 668 | 3.9552 | 2642.0437
Floor
246 | Floor Insulation (If.Req) | 276 | M2 | 0% | 276 | 15.8775 | 4382.1779
Ceiling
247 | Ceiling Insulation (If.Req) | 289 | M2 | 0% | 289 | 15.8775 | 4588.5848
Roof
248 | Roof Sarking/ Insulation | 270 | M2 | 0% | 270 | 15.8775 | 4286.9131
Sub Total | [7 empty] | 36826.9172
Timber/Steel Stair Frame
249 | Internal Timber Stair Finish Already Cover In Flooring - Tread (250mm Wide x 16 EA) - Riser (180mm H x 17 EA) | 4 | EA | 0% | 4 | 369.1238 | 1476.4954
Sub Total | [7 empty] | 1476.4954
Masonry Supply & Install
Block Wall
Basement
250 | (190mm Thick) Block Wall 'BLK1' Reinforced w/ (3.4 LM & 1350mm H) - 1N16 End Vert, N16 Vert & N12-200 Horiz, Each Face, Lap 600 - Filled w/ 25 MPa Concrete, 6mm Aggregate | 4.6305 | M2 | 0% | 4.6305 | 85.0148 | 393.6608
251 | (190mm Thick) Block Wall 'BLK1' Reinforced w/ (21.3 LM & 2600mm H) - 1N16 End Vert, N16 Vert & N12-200 Horiz, Each Face, Lap 600 - Filled w/ 25 MPa Concrete, 6mm Aggregate | 55.458 | M2 | 0% | 55.458 | 85.0148 | 4714.7486
252 | (190mm Thick) Block Wall 'BLK1' Reinforced w/ (5.3 LM & 3150mm H) - 1N16 End Vert, N16 Vert & N12-200 Horiz, Each Face, Lap 600 - Filled w/ 25 MPa Concrete, 6mm Aggregate | 16.7265 | M2 | 0% | 16.7265 | 85.0148 | 1421.9994
Block Lintel
253 | (190mm H) Reinforced Block Lintel | 1.74 | M | 0% | 1.74 | 51.0787 | 88.877
Ground Floor
254 | (140mm Thick) Reinforced Concrete Block Retaining Wall (4.7 LM & 100mm H ) | 0.467 | M2 | 0% | 0.467 | 72.4781 | 33.8473
255 | (140mm Thick) Reinforced Concrete Block Retaining Wal (2.2 LM & 300mm H) | 0.66 | M2 | 0% | 0.66 | 72.4781 | 47.8355
256 | (140mm Thick) Reinforced Concrete Block Retaining Wall (8.8 LM & 400mm H) | 3.52 | M2 | 0% | 3.52 | 72.4781 | 255.1228
257 | (140mm Thick) Reinforced Concrete Block Retaining Wall (11.4 LM & 500mm H) | 5.685 | M2 | 0% | 5.685 | 72.4781 | 412.0378
258 | (140mm Thick) Reinforced Concrete Block Retaining Wall (7.1 LM & 600mm H) | 4.23 | M2 | 0% | 4.23 | 72.4781 | 306.5822
259 | (140mm Thick) Reinforced Concrete Block Retaining Wall (3.4 LM & 700mm H) | 2.38 | M2 | 0% | 2.38 | 72.4781 | 172.4978
260 | (140mm Thick) Reinforced Concrete Block Retaining Wall (10.2 LM & 1000mm H) | 10.24 | M2 | 0% | 10.24 | 72.4781 | 742.1754
261 | (140mm Thick) Reinforced Concrete Block Retaining Wall (8.2 LM & 1200mm H) | 9.78 | M2 | 0% | 9.78 | 72.4781 | 708.8355
262 | (140mm Thick) Reinforced Concrete Block Retaining Wall (4.5 LM & 1400mm H) | 6.3 | M2 | 0% | 6.3 | 72.4781 | 456.6118
263 | (140mm Thick) Reinforced Concrete Block Retaining Wall (18.5 LM & 1700mm H) | 31.501 | M2 | 0% | 31.501 | 72.4781 | 2283.1316
264 | (140mm Thick) Reinforced Concrete Block Retaining Wall (4.3 LM & 2000mm H) | 8.56 | M2 | 0% | 8.56 | 72.4781 | 620.4123
Sub Total | [7 empty] | 12658.3759
Scaffold
265 | Ground Floor Scaffolding | 81.66 | M | 0% | 81.66 | 44.9553 | 3671.0482
266 | First Floor Scaffolding | 97.28 | M | 0% | 97.28 | 44.9553 | 4373.2496
Sub Total | [7 empty] | 8044.2978
Aluminum Windows & Doors
Glazed Door
External
267 | (2400 x 2000) Aluminium Framed Glazed Door | 4 | EA | 0% | 4 | 9955.4465 | 39821.7861
268 | (2400 x 2100) Aluminium Framed Glazed Door | 1 | EA | 0% | 1 | 10453.2189 | 10453.2189
269 | (2400 x 2800) Aluminium Framed Glazed Door | 1 | EA | 0% | 1 | 13937.6251 | 13937.6251
270 | (2400 x 2900) Aluminium Framed Glazed Door | 1 | EA | 0% | 1 | 14435.3975 | 14435.3975
271 | (2400 x 3000) Aluminium Framed Glazed Door | 1 | EA | 0% | 1 | 14933.1698 | 14933.1698
272 | (2400 x 3200) Aluminium Framed Glazed Door | 2 | EA | 0% | 2 | 15928.7144 | 31857.4289
273 | (2400 x 3350) Aluminium Framed Glazed Door | 1 | EA | 0% | 1 | 16675.3729 | 16675.3729
274 | (2400 x 3400) Aluminium Framed Glazed Door | 1 | EA | 0% | 1 | 16924.2591 | 16924.2591
275 | (2400 x 3500) Aluminium Framed Glazed Door | 1 | EA | 0% | 1 | 17422.0314 | 17422.0314
Window
276 | (2200 x 600) Aluminium Frame Glazed Fixed Window - Glass Type: Clear Glass 'CG' | 2 | EA | 0% | 2 | 969.1279 | 1938.2559
277 | (700 x 1500) Aluminium Framed Glazed Awning Window - Glass Type: Clear Glass 'CG' | 5 | EA | 0% | 5 | 770.8972 | 3854.4862
278 | (1600 x 2200) Aluminium Framed Glazed Awning & Fixed Window - Glass Type: Clear Glass 'CG' | 1 | EA | 0% | 1 | 2584.3412 | 2584.3412
279 | (600 x 2100) Aluminium Framed Glazed Fixed Window - Glass Type: Clear Glass 'CG' | 6 | EA | 0% | 6 | 925.0767 | 5550.4601
280 | (700 x 1200) Aluminium Framed Glazed Awning Window - Glass Type: Clear Glass 'CG' | 1 | EA | 0% | 1 | 616.7178 | 616.7178
281 | (1600 x 2200) Aluminium Framed Glazed Awning & Fixed Window - Glass Type: Clear Glass 'CG' - Glass Type: Obscured Glass 'OG' | 1 | EA | 0% | 1 | 2584.3412 | 2584.3412
282 | (2100 x 2500) Aluminium Framed Glazed Awning & Fixed Window - Glass Type: Clear Glass 'CG' - Glass Type: Obscured Glass 'OG' | 8 | EA | 0% | 8 | 3854.4862 | 30835.8893
283 | (600 x 2100) Aluminium Framed Glazed Fixed & Awning Window - Glass Type: Clear Glass 'CG' - Glass Type: Obscured Glass 'OG' | 12 | EA | 0% | 12 | 925.0767 | 11100.9201
284 | (700 x 800) Aluminium Framed Glazed Awning Window - Glass Type: Clear Glass 'CG' | 3 | EA | 0% | 3 | 411.1452 | 1233.4356
285 | (600 x 2100) Aluminium Framed Glazed Fixed & Awning Window - Glass Type: Clear Glass 'CG' | 2 | EA | 0% | 2 | 925.0767 | 1850.1534
Sub Total | [7 empty] | 238609.2904
Roofing (Metal/Tiles)
Roofing
Roof Covering
286 | Lower Metal Roof Covering | 8.6 | M2 | 0% | 8.6 | 74.9456 | 644.5317
287 | Upper Metal Roof Covering | 260.71 | M2 | 0% | 260.71 | 74.9456 | 19539.0549
Capping & Flashing
288 | Parapet Capping | 130.62 | M | 0% | 130.62 | 22.1012 | 2886.8541
289 | Apron Flashing | 15.61 | M | 0% | 15.61 | 23.3244 | 364.0939
290 | Parapet Flashing | 103.03 | M | 0% | 103.03 | 21.2511 | 2189.5029
291 | Z Flashing | 51.06 | M | 0% | 51.06 | 24.6098 | 1256.5781
292 | Barge Flashing | 3.22 | M | 0% | 3.22 | 23.9257 | 77.0406
293 | Skylight Flashing | 3.56 | M | 0% | 3.56 | 25.6257 | 91.2276
Box Gutter
294 | (150mm Wide) Box Gutter | 51.06 | M | 0% | 51.06 | 29.0818 | 1484.9163
Rain Water Head
295 | Rain Water Head | 5 | EA | 0% | 5 | 297.4232 | 1487.1159
Eave Gutter
296 | Eave Gutter & Fascia | 4.81 | M | 0% | 4.81 | 29.4918 | 141.8555
Downpipe
297 | (100mm.Dia) Lower Roof Downpipe | 6 | EA | 0% | 6 | 60.0622 | 360.3734
298 | (100mm.Dia) Upper Roof Down Pipe | 9 | EA | 0% | 9 | 61.0902 | 549.8122
Sub Total | [7 empty] | 31072.9572
Solar Panel
Solar Panels
299 | (1950 x 1200) Solar Panel | 8 | EA | 0% | 8 | 465.183 | 3721.4643
Sub Total | [7 empty] | 3721.4643
Skylights
300 | (900 x 900) Skylight | 1 | EA | 0% | 1 | 556.4907 | 556.4907
Sub Total | [7 empty] | 556.4907
Cladding
External Cladding
301 | Foam Cladding | 222.5 | M2 | 0% | 222.5 | 33.0602 | 7355.8856
302 | Horizontal Timber Wall Cladding or Similar | 117.8 | M2 | 0% | 117.8 | 47.8618 | 5638.1153
303 | Black Metal Wall Sheet Cladding or Similar | 81.6 | M2 | 0% | 81.6 | 55.0314 | 4490.559
Sub Total | [7 empty] | 17484.5599
Render
Render
304 | White Render or Similar - Substrate: Foam Cladding | 208.1 | M2 | 0% | 208.1 | 36.0202 | 7495.7953
305 | White Render or Similar - Substrate: Block Wall | 22.02 | M2 | 0% | 22.02 | 36.0202 | 793.1639
Sub Total | [7 empty] | 8288.9592
Plasterboard
Walls
Basement
306 | 10mm Plasterboard Wall Lining w/ Furring Channel | 354.3 | M2 | 0% | 354.3 | 21.5335 | 7629.3354
Ground Floor
307 | 10mm Plasterboard Wall Lining | 702 | M2 | 0% | 702 | 21.5335 | 15116.5494
308 | 10mm Moisture Resistant Plasterboard Wall Lining | 208 | M2 | 0% | 208 | 23.4507 | 4877.7453
First Floor
309 | 10mm Plasterboard Wall Lining | 702 | M2 | 0% | 702 | 21.5335 | 15116.5494
310 | 10mm Moisture Resistant Plasterboard Wall Lining | 200 | M2 | 0% | 200 | 23.4507 | 4690.1397
Ceiling
Basement
Internal Lining
311 | 10mm Plasterboard Ceiling Lining | 323.76 | M2 | 0% | 323.76 | 21.5335 | 6971.7009
External Lining
312 | External Soffit Lining | 5.35 | M2 | 0% | 5.35 | 20.0279 | 107.1494
Cornice
313 | Cornice | 111.11 | M | 0% | 111.11 | 17.507 | 1945.2047
Ground Floor
Internal Lining
314 | 10mm Plasterboard Ceiling Lining | 216.22 | M2 | 0% | 216.22 | 21.5335 | 4655.9834
315 | 10mm Moisture Resistant Plasterboard Ceiling Lining | 28.53 | M2 | 0% | 28.53 | 23.4507 | 669.0484
External Lining
316 | External Soffit Lining | 6.22 | M2 | 0% | 6.22 | 20.0279 | 124.5736
Cornice
317 | Cornice | 294.24 | M | 0% | 294.24 | 17.507 | 5151.2647
First Floor
Internal Lining
318 | 10mm Plasterboard Ceiling Lining | 208.87 | M2 | 0% | 208.87 | 21.5335 | 4497.7118
319 | 10mm Moisture Resistant Plasterboard Ceiling Lining | 33.62 | M2 | 0% | 33.62 | 23.4507 | 788.4125
External Lining
320 | External Soffit Lining | 4.49 | M2 | 0% | 4.49 | 20.0279 | 89.9253
Cornice
321 | Cornice | 353.22 | M | 0% | 353.22 | 17.507 | 6183.8286
Sub Total | [7 empty] | 78615.1226
External Balustrades
322 | Internal Stair Handrail | 40.91 | M | 0% | 40.91 | 203.7602 | 8335.8281
323 | (1000mm H) Internal Stair Balustrade | 12.07 | M | 0% | 12.07 | 349.6576 | 4220.3672
324 | (1000mm H) External Balcony Glass Balustrade | 4.25 | M | 0% | 4.25 | 349.6576 | 1486.0448
325 | (1700mm H) External Balcony Glass Balustrade - Glass Type: Obscured Glass 'OG' | 8.71 | M | 0% | 8.71 | 364.4736 | 3174.5651
Sub Total | [7 empty] | 17216.8052
Sundry Metalwork (e.g. Garage Door)
Garage Door
326 | (2250 x 3500) Panel Lift Garage Door | 1 | EA | 0% | 1 | 5577.4152 | 5577.4152
Sub Total | [7 empty] | 5577.4152
Door & Hardware Supply & Install
Timber Doors
External Doors
327 | (2400 x 920) External Single Timber Door | 7 | EA | 0% | 7 | 1254.1867 | 8779.3072
Internal Door
328 | (2400 x 1020) Internal Single Timber Door | 1 | EA | 0% | 1 | 1390.5114 | 1390.5114
329 | (2400 x 1180) Internal Double Timber Door | 1 | EA | 0% | 1 | 1608.6308 | 1608.6308
330 | (2400 x 1440) Internal Double Timber Door | 1 | EA | 0% | 1 | 1963.0749 | 1963.0749
331 | (2400 x 720) Internal Single Timber Door | 7 | EA | 0% | 7 | 981.5375 | 6870.7622
332 | (2400 x 820) Internal Single Cavity Timber Door | 6 | EA | 0% | 6 | 1117.8621 | 6707.1726
333 | (2400 x 820) Internal Single Timber Door | 24 | EA | 0% | 24 | 1117.8621 | 26828.6904
334 | (2400 x (3)500) Joinery Door | 27 | EA | 0% | 27 | 1363.2465 | 36807.6545
335 | (2400 x (3)400) Joinery Door | 1 | EA | 0% | 1 | 1635.8958 | 1635.8958
336 | (2400 x (3)900) Joinery Door | 2 | EA | 0% | 2 | 3680.7655 | 7361.5309
337 | (2400 x (3)800) Joinery Door | 3 | EA | 0% | 3 | 3271.7915 | 9815.3745
Door Hardware
External Doors
338 | External Single Timber Door Hardware | 7 | EA | 0% | 7 | 762.3388 | 5336.3715
Internal Door
339 | Internal Single Timber Door Hardware | 32 | EA | 0% | 32 | 603.9255 | 19325.6151
340 | Internal Double Timber Door Hardware | 2 | EA | 0% | 2 | 769.0798 | 1538.1596
341 | Internal Single Cavity Timber Door Hardware | 6 | EA | 0% | 6 | 640.7818 | 3844.6911
342 | Joinery Door Hardware | 33 | EA | 0% | 33 | 550.3009 | 18159.9291
Sub Total | [7 empty] | 157973.3717
Carpentry Fitout
Timber Skirting
Ground Floor
343 | Timber Skirting | 165.95 | M | 0% | 165.95 | 16.4223 | 2725.2813
First Floor
344 | Timber Skirting | 198.61 | M | 0% | 198.61 | 16.4223 | 3261.6338
Architraves
345 | Door Architraves | 589 | M | 0% | 589 | 16.816 | 9904.624
346 | Window Architraves | 243 | M | 0% | 243 | 19.1098 | 4643.6717
Sub Total | [7 empty] | 20535.2108
Waterproofing
Floor
Ground Floor
347 | Wet Area Floor Waterproofing | 29.12 | M2 | 0% | 29.12 | 11.6509 | 339.275
First Floor
348 | Wet Area Floor Waterproofing | 34.22 | M2 | 0% | 34.22 | 11.6509 | 398.6948
349 | External Floor Waterproofing | 22.12 | M2 | 0% | 22.12 | 11.6509 | 257.7185
Wall
Ground Floor
350 | Wet Area Wall Waterproofing | 30.11 | M2 | 0% | 30.11 | 11.6509 | 350.8094
First Floor
351 | Wet Area Wall Waterproofing | 48.31 | M2 | 0% | 48.31 | 11.6509 | 562.8563
Sub Total | [7 empty] | 1909.3541
Tiling (Supply & Install)
Floor
Ground Floor
352 | Wet Area Tile Flooring | 29.12 | M2 | 0% | 29.12 | 151.4879 | 4411.3273
First Floor
353 | Wet Area Tile Flooring | 34.22 | M2 | 0% | 34.22 | 151.4879 | 5183.9155
354 | External Tile Flooring | 22.12 | M2 | 0% | 22.12 | 151.4879 | 3350.9121
Skirting
Ground Floor
355 | Wet Area Tile Skirting | 47.53 | M | 0% | 47.53 | 64.8771 | 3083.608
First Floor
356 | Wet Area Tile Skirting | 42.33 | M | 0% | 42.33 | 64.8771 | 2746.2471
Wall
Ground Floor
357 | Wet Area Full Height Wall Tile | 30.11 | M2 | 0% | 30.11 | 151.4879 | 4561.3003
First Floor
358 | Wet Area Full Height Wall Tile | 48.31 | M2 | 0% | 48.31 | 151.4879 | 7318.3799
Sub Total | [7 empty] | 30655.6902
Flooring
Concrete
Basement
359 | Sealed Concrete Flooring | 333.6 | M2 | 0% | 333.6 | 54.579 | 18207.5624
360 | Internal Caulking | 106.06 | M | 0% | 106.06 | 4.9315 | 523.0397
Timber
Ground Floor
361 | Timber Flooring | 163.3 | M2 | 0% | 163.3 | 78.3285 | 12791.0434
First Floor
362 | Timber Flooring | 92.2 | M2 | 0% | 92.2 | 78.3285 | 7221.8873
Carpet
Ground Floor
363 | Carpet Flooring | 54.55 | M2 | 0% | 54.55 | 41.469 | 2262.1361
First Floor
364 | Carpet Flooring | 135.77 | M2 | 0% | 135.77 | 41.469 | 5630.2516
Sub Total | [7 empty] | 46635.9206
Painting
Walls
Basement
365 | Paint Plasterboard Wall Lining | 354.3 | M2 | 0% | 354.3 | 22.0709 | 7819.7241
Ground Floor
366 | Paint Plasterboard Wall Lining | 635 | M2 | 0% | 635 | 22.0709 | 14015.0291
367 | Paint Moisture Resistant Plasterboard Wall Lining | 151.3 | M2 | 0% | 151.3 | 22.0709 | 3339.329
First Floor
368 | Paint Plasterboard Wall Lining | 625.2 | M2 | 0% | 625.2 | 22.0709 | 13798.7342
369 | Paint Moisture Resistant Plasterboard Wall Lining | 124.9 | M2 | 0% | 124.9 | 22.0709 | 2756.6569
Ceiling
Basement
Internal Lining
370 | Paint Plasterboard Ceiling Lining | 323.76 | M2 | 0% | 323.76 | 22.0709 | 7145.6785
External Lining
371 | Paint External Soffit Lining | 5.35 | M2 | 0% | 5.35 | 22.0709 | 118.0794
Cornice
372 | Paint Cornice | 111.11 | M | 0% | 111.11 | 7.4983 | 833.1408
Ground Floor
Internal Lining
373 | Paint Plasterboard Ceiling Lining | 216.22 | M2 | 0% | 216.22 | 22.0709 | 4772.1726
374 | Paint Moisture Resistant Plasterboard Ceiling Lining | 28.53 | M2 | 0% | 28.53 | 22.0709 | 629.6831
External Lining
375 | Paint External Soffit Lining | 6.22 | M2 | 0% | 6.22 | 22.0709 | 137.2811
Cornice
376 | Paint Cornice | 294.24 | M | 0% | 294.24 | 7.4983 | 2206.3123
First Floor
Internal Lining
377 | Paint Plasterboard Ceiling Lining | 208.87 | M2 | 0% | 208.87 | 22.0709 | 4609.9514
378 | Paint Moisture Resistant Plasterboard Ceiling Lining | 33.62 | M2 | 0% | 33.62 | 22.0709 | 742.0241
External Lining
379 | Paint External Soffit Lining | 4.49 | M2 | 0% | 4.49 | 22.0709 | 99.0984
Cornice
380 | Paint Cornice | 353.22 | M | 0% | 353.22 | 7.4983 | 2648.5645
Timber Skirting
Ground Floor
381 | Paint Timber Skirting | 47.53 | M | 0% | 47.53 | 7.4983 | 356.3962
First Floor
382 | Paint Timber Skirting | 42.33 | M | 0% | 42.33 | 7.4983 | 317.4048
Architraves
383 | Paint Door Architraves | 589 | M | 0% | 589 | 7.4983 | 4416.5237
384 | Paint Window Architraves | 243 | M | 0% | 243 | 7.4983 | 1822.0972
Doors
External Doors
385 | Paint External Single Timber Door | 7 | EA | 0% | 7 | 159.0541 | 1113.3786
Internal Door
386 | Paint Internal Single Timber Door | 32 | EA | 0% | 32 | 159.0541 | 5089.7306
387 | Paint Internal Double Timber Door | 2 | EA | 0% | 2 | 308.1082 | 616.2163
388 | Paint Internal Single Cavity Timber Door | 6 | EA | 0% | 6 | 159.0541 | 954.3245
389 | Paint Joinery Door | 33 | EA | 0% | 33 | 159.0541 | 5248.7846
Sub Total | [7 empty] | 85606.3159
Joinery
Joinery
Storage
390 | (610mm Deep) Storage Cupboards | 24.63 | M | 0% | 24.63 | 708.8292 | 17458.4621
Built In Robe
391 | (500mm Deep) Built In Robe | 35.46 | M | 0% | 35.46 | 581.0401 | 20603.6814
Kitchen
392 | (700mm Deep) Kitchen Base Cabinets | 9.07 | M | 0% | 9.07 | 813.4561 | 7378.047
393 | (350mm Deep) Kitchen Wall Mounted Cabinets | 8.99 | M | 0% | 8.99 | 406.7281 | 3656.4852
394 | (700mm Deep) Kitchen Cupboards | 1.42 | M | 0% | 1.42 | 813.4561 | 1155.1077
395 | (600mm Deep) Kitchen Cupboards | 1 | M | 0% | 1 | 697.2481 | 697.2481
396 | (750mm Deep) Fridge Enclosure | 1.01 | M | 0% | 1.01 | 871.5601 | 880.2757
397 | (700mm Deep) Fridge Enclosure | 3.09 | M | 0% | 3.09 | 813.4561 | 2513.5794
398 | (2450 x 900) Kitchen Island | 1 | EA | 0% | 1 | 1082.6514 | 1082.6514
399 | (2850 x 900) Kitchen Island | 2 | EA | 0% | 2 | 1259.4108 | 2518.8216
400 | (2350 x 900) Kitchen Island | 1 | EA | 0% | 1 | 1038.4615 | 1038.4615
Vanity
401 | (600mm Deep) Vanity Base Cabinets | 11.76 | M | 0% | 11.76 | 697.2481 | 8199.6377
402 | (500mm Deep) Vanity Base Cabinets | 0.89 | M | 0% | 0.89 | 581.0401 | 517.1257
Benchtop
Kitchen
403 | (700mm Wide) Kitchen Benchtop | 9 | M | 0% | 9 | 681.1424 | 6130.2816
Vanity
404 | (500mm Wide) Vanity Benchtop | 0.9 | M | 0% | 0.9 | 584.9811 | 526.483
405 | (600mm Wide) Vanity Benchtop | 11.64 | M | 0% | 11.64 | 612.2268 | 7126.3201
Splash back
Kitchen
406 | (600mm H) Kitchen Splash back | 5.418 | M2 | 0% | 5.418 | 142.2706 | 770.8222
Sub Total | [7 empty] | 82253.4914
Shower Screens/ Partition
407 | (850 x 850) Shower Screen | 4 | EA | 0% | 4 | 874.6208 | 3498.4834
408 | (1300 x 850) Shower Screen | 2 | EA | 0% | 2 | 1265.0915 | 2530.1829
409 | (2100mm H) Shower Partition | 3.93 | M | 0% | 3.93 | 812.7364 | 3194.0542
410 | (1050 x 750) Shower Screen | 4 | EA | 0% | 4 | 953.3723 | 3813.4891
Sub Total | [7 empty] | 13036.2096
PC Items
Fixture
411 | Vanity | 14 | EA | 0% | 14 | 956.6166 | 13392.6317
412 | Laundry Trough | 4 | EA | 0% | 4 | 588.1516 | 2352.6062
413 | Floor Waste | 22 | EA | 0% | 22 | 335.8699 | 7389.1384
414 | Water Closet | 13 | EA | 0% | 13 | 796.0437 | 10348.5687
415 | Kitchen Sink | 4 | EA | 0% | 4 | 604.9198 | 2419.6791
Tapware
416 | Vanity Mixer | 14 | EA | 0% | 14 | 211.2627 | 2957.6776
417 | Laundry Trough Mixer | 4 | EA | 0% | 4 | 185.7143 | 742.8573
418 | Shower Head w/ Mixer | 13 | EA | 0% | 13 | 251.9446 | 3275.2795
419 | Kitchen Sink Mixer | 4 | EA | 0% | 4 | 207.8922 | 831.5688
Accessories
420 | Mirror | 14 | EA | 0% | 14 | 264.3143 | 3700.4001
421 | Soap Dispenser | 14 | EA | 0% | 14 | 239.9119 | 3358.7667
422 | Towel Rail | 13 | EA | 0% | 13 | 138.797 | 1804.3613
423 | Toilet Roll Holder | 13 | EA | 0% | 13 | 144.3415 | 1876.4394
Sub Total | [7 empty] | 54449.9748
Appliances
424 | Fridge | 4 | EA | 0% | 4 | 2126.0076 | 8504.0302
425 | Oven | 4 | EA | 0% | 4 | 1388.8832 | 5555.5328
426 | Cook Top | 4 | EA | 0% | 4 | 2886.167 | 11544.6682
427 | Range Hood | 4 | EA | 0% | 4 | 1062.3263 | 4249.3051
428 | Dish Washer | 4 | EA | 0% | 4 | 1147.6918 | 4590.7671
429 | Washing Machine & Dryer | 4 | EA | 0% | 4 | 1795.3856 | 7181.5424
Sub Total | [7 empty] | 41625.8458
Hydraulic Services
430 | Allowance For Plumbing Services | 944 | M2 | 0% | 944 | 79.0099 | 74585.3645
431 | Allowance For Stormwater & Drainage Services | 944 | M2 | 0% | 944 | 46.8115 | 44190.0749
BASEMENT LEVEL
CONDUITS
ELECTRICAL PVC CONDUITS
432 | Electrical PVC Conduit 'E' | 4 | M | 0% | 4 | 21.7514 | 87.0055
PIPING
UPVC STORMWATER PIPE
433 | (100mm.Dia) UPVC Stormwater Pipe | 49 | M | 0% | 49 | 12.3428 | 604.7992
434 | (225mm.Dia) UPVC Stormwater Pipe | 16 | M | 0% | 16 | 26.1108 | 417.7728
FIXTURES
435 | (200 x 150) Grated Trench 'GT' | 4 | M | 0% | 4 | 28.1864 | 112.7456
436 | Spoon Drain To Floor Waster | 5 | EA | 0% | 5 | 432.2661 | 2161.3306
437 | (150mm.Dia) Inspection Opening 'IO' | 6 | EA | 0% | 6 | 319.1186 | 1914.7114
438 | (150mm.Dia) Galvanized Pipe Sleeve | 1 | EA | 0% | 1 | 61.6464 | 61.6464
439 | Pump Discharge w/ EPOXY - Wall Strip Drain Discharge (1 EA) - Main Ring Pipe (1 EA) - Inspection Opening (1 EA) - Volclay Water Stop RX101 (1 EA) - Nylex Strip Drain (1 EA) - (70 x 90) Dish Drain (1 EA) - Spray Wall System (1 EA) | 1 | EA | 0% | 1 | 1052.2998 | 1052.2998
PITS
440 | Pit 6 Matching GL | 1 | EA | 0% | 1 | 287.6842 | 287.6842
441 | (600 x 600) Stormwater Pit 'B1' - Depth: 0.50m | 1 | EA | 0% | 1 | 825.623 | 825.623
442 | (900 x 900) Stormwater Pump Pit 'PP1' - Depth: 2.00m - Galvanized Steel Grated Cover Fixed w/ Padlocks For Secure Cover (1 EA) - (80mm.Dia) Check Valve 'CV' (2 EA) - (80mm.Dia) Union (2 EA) - (80mm.Dia) Gate Valve (2 EA) - (2m) S/S Pump Lifting Chain (2 EA) - (80mm.Dia) PVC Pipe Riser (2 EA & 2m H) - Dual Submersible Electric Pump Set (2 EA) - Seal Around All Penetration w/ Epoxy Resin (1 EA) - Mercury Float Switch (1 EA) | 1 | EA | 0% | 1 | 2308.9626 | 2308.9626
PANELS
443 | Pump Control Panel | 1 | EA | 0% | 1 | 1081.7616 | 1081.7616
GROUND LEVEL
PIPING
UPVC STORMWATER PIPE
444 | (100mm.Dia) UPVC Stormwater Pipe | 25 | M | 0% | 25 | 12.3428 | 308.571
445 | (150mm.Dia) UPVC Stormwater Pipe | 74 | M | 0% | 74 | 13.7199 | 1015.2701
446 | (450mm.Dia) UPVC Stormwater Pipe | 15 | M | 0% | 15 | 118.7021 | 1780.5322
447 | (525mm.Dia) UPVC Stormwater Pipe | 29 | M | 0% | 29 | 135.9562 | 3942.731
FITTING
BENDS
448 | (100mm.Dia & 45 Degree) UPVC Stormwater Pipe Bend | 1 | EA | 0% | 1 | 31.5968 | 31.5968
TEES
449 | (100mm.Dia & 45 Degree) UPVC Stormwater Pipe Tee | 1 | EA | 0% | 1 | 31.5968 | 31.5968
450 | (150mm.Dia & 90 Degree) UPVC Stormwater Pipe Tee | 5 | EA | 0% | 5 | 36.4897 | 182.4486
451 | (525mm.Dia & 90 Degree) UPVC Stormwater Pipe Tee | 1 | EA | 0% | 1 | 137.1286 | 137.1286
FIXTURES
452 | (150mm.Dia) Inspection Opening 'IO' | 2 | EA | 0% | 2 | 29.5442 | 59.0885
PITS
453 | (1200x600+600 x 600) Stormwater Pit 'P1' - Depth: 0.86m - (150mm.Dia) Long Pe Pressure Pipe (1 EA) - Hydrotite Seal Around Perimeter Of Pipe (6 EA) - (600 x 600) Medium Duty Concrete Pit Cover (1 EA) - Galvanized Step Iron (12 EA) - Orifice, Install 100mm, Long, PE Pressure Pipe, SDR11, PE100, PN16, ID 51.0mm, DN 63mm (1 EA) - (1200 x 600) Medium Duty Concrete Pit Cover (1 EA) - 6mm Thick Stainless Steel Plate (1 EA) - (63mm.Dia) Sharp EDGE Orifice (1 EA) - Trash Grate In Accordance (1 EA) | 1 | EA | 0% | 1 | 3134.3235 | 3134.3235
454 | (600 x 600) Stormwater Pit 'P2' - Depth: 1.30m | 1 | EA | 0% | 1 | 2146.6198 | 2146.6198
455 | (600 x 600) Stormwater Pit 'P3' - Depth: 0.50m | 1 | EA | 0% | 1 | 825.623 | 825.623
456 | (450 x 450) Stormwater Pit 'P4' - Depth: 0.47m | 1 | EA | 0% | 1 | 647.6938 | 647.6938
457 | (600 x 600) Stormwater Pit 'P5' - Depth: 0.87m | 1 | EA | 0% | 1 | 1436.584 | 1436.584
458 | (600 x 600) Stormwater Pit 'P6' - Depth: 0.93m | 1 | EA | 0% | 1 | 1535.6588 | 1535.6588
Sub Total | [7 empty] | 146907.2483
Electrical Services
459 | Allowance For Electrical Services | 944 | M2 | 0% | 944 | 72.5702 | 68506.3066
Sub Total | [7 empty] | 68506.3066
Mechanical Services
460 | Allowance For Mechanical Services | 944 | M2 | 0% | 944 | 70.5062 | 66557.8906
Hot Water System
461 | Hot Water System on Roof | 4 | EA | 0% | 4 | 1276.6502 | 5106.601
Sub Total | [7 empty] | 71664.4915
Fire Services
462 | Allowance For Fire Services | 944 | M2 | 0% | 944 | 62.5805 | 59075.9731
Sub Total | [7 empty] | 59075.9731
Civil Works
External Finish
463 | External Concrete Floor Finish | 46.9 | M2 | 0% | 46.9 | 49.9522 | 2342.7593
464 | External Stair Finish | 3.1 | M2 | 0% | 3.1 | 49.9522 | 154.8519
Sleeper Retaining Wall
465 | (900mm H) Sleeper Raised Garden Bed (32.8 LM) | 29.484 | M2 | 0% | 29.484 | 28.896 | 851.9697
466 | (1000mm H) Sleeper Raised Garden Bed (15 LM) | 14.97 | M2 | 0% | 14.97 | 28.896 | 432.5731
467 | (1000mm H) Sleeper Retaining Wall (25.6 LM) | 25.62 | M2 | 0% | 25.62 | 28.896 | 740.3155
468 | (1150mm H) Sleeper Retaining Wall (11.2 LM) | 12.857 | M2 | 0% | 12.857 | 33.2304 | 427.2433
469 | (2400mm H) Sleeper Retaining Wall (14.1 LM) | 33.744 | M2 | 0% | 33.744 | 69.3504 | 2340.1599
Fence
470 | (1800mm H) Pailing Fence | 7.74 | M | 0% | 7.74 | 52.0128 | 402.5791
Screen
471 | (150mm H) Timber Private Screen | 7.25 | M | 0% | 7.25 | 43.344 | 314.244
472 | (1500mm H) Timber Screen | 10.01 | M | 0% | 10.01 | 43.344 | 433.8734
Mail Box
473 | Mail Box | 1 | EA | 0% | 1 | 503.244 | 503.244
Bike Racks
474 | Bike Racks | 4 | EA | 0% | 4 | 204.6312 | 818.5248
Bins
475 | Bins 80L | 8 | EA | 0% | 8 | 118.4224 | 947.379
476 | Bins 120L | 4 | EA | 0% | 4 | 168.9313 | 675.7253
Pavers
477 | (800 x 350) Pavers | 4 | EA | 0% | 4 | 397.4666 | 1589.8665
478 | (1000 x 350) Pavers | 32 | EA | 0% | 32 | 496.8333 | 15898.665
Foldable Clothes Line
479 | (1200 x 1750) Foldable Clothes Line 'FCL' | 4 | EA | 0% | 4 | 681.6232 | 2726.4928
Bollard
480 | Lighting Bollard To Pedestrian Access way | 4 | EA | 0% | 4 | 553.2479 | 2212.9916
Sub Total | [7 empty] | 33813.4582
Landscaping
Grass Turf
481 | Grass Turf | 121.03 | M2 | 0% | 121.03 | 26.5676 | 3215.4766
landscaping Area
482 | landscaping Area | 43.49 | M2 | 0% | 43.49 | 25.6298 | 1114.6383
Mulch Garden Bed
483 | Mulch Garden Bed | 123.01 | M2 | 0% | 123.01 | 29.6927 | 3652.5015
Tree
484 | Canopy Tree | 2 | EA | 0% | 2 | 307.3218 | 614.6437
485 | Medium Tree | 1 | EA | 0% | 1 | 256.7644 | 256.7644
486 | Tree | 1 | EA | 0% | 1 | 431.8448 | 431.8448
Sub Total | [7 empty] | 9285.8692
Window Shroud
Window Shroud
487 | (100mm Wide) Window Shroud | 2.42 | M | 0% | 2.42 | 20.8001 | 50.3361
488 | (200mm Wide) Window Shroud | 15.92 | M | 0% | 15.92 | 41.6348 | 662.8263
489 | (300mm Wide) Window Shroud | 1.32 | M | 0% | 1.32 | 62.4522 | 82.4369
490 | (500mm Wide) Window Shroud | 16.65 | M | 0% | 16.65 | 104.087 | 1733.0492
491 | (1000mm Wide) Window Shroud | 4.83 | M | 0% | 4.83 | 208.1741 | 1005.4808
492 | (1200mm Wide) External Awning | 8.75 | M | 0% | 8.75 | 249.8089 | 2185.8278
Sub Total | [7 empty] | 5719.9572
PROJECTED COST | [7 empty] | 1874641.6433
SUBTOTAL | [7 empty] | 1874641.6433
OVERHEADS & PROFITS | [6 empty] | 25% | 468660.4108
INSURANCES | [6 empty] | 3% | 56239.2493
CONTINGENCY | [6 empty] | 7% | 131224.915
TOTAL COST (EXCL. GST) | [7 empty] | 4405407.8617
Inclusion & Exclusions: